## Blad1
Lofthus frukt og saft |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
Project Plan GANTT |  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
PREPARATIONS | bar: Week 1 Mon to Week 2 Fri
Collect existing brand info from customer | Project manager | bar: Week 1 Mon
Make design examples/tiles | Visual designer & Content specialist | bar: Week 1 Tue to Week 1 Thu
Get approval from customer | Project Manager
Make page mockup design | Visual designer & Content specialist | bar: Week 1 Fri to Week 2 Thu
Get final approval from customer | Project manager
CUSTOMER PROFILE | bar: Week 3 Mon to Week 4 Fri
Setup Profile page | Back-end & Front-end | bar: Week 3 Mon to Week 3 Tue
Setup log in page | Back-end & Front-end | bar: Week 3 Mon to Week 3 Tue
Collect customer data in database | Back-end | bar: Week 3 Wed
Collect purchase data in database | Back-end | bar: Week 3 Thu
Setup purchase history view | Back-end & Front-end | bar: Week 3 Fri to Week 4 Mon
Create page search function | Back-end & Front-end | bar: Week 4 Tue to Week 4 Wed
Create menu & navigation | Front-end | bar: Week 4 Wed to Week 4 Thu
Customer presentation & approval | Project manager
COMPANY INFORMATION | bar: Week 3 Mon to Week 6 Tue
Collect company info | Content specialist | bar: Week 3 Mon to Week 3 Tue
Create text content | Content specialist | bar: Week 3 Wed to Week 4 Wed
Create image content | Visual designer | bar: Week 3 Mon to Week 4 Wed
Setup design | Visual designer
Create company blog & article page with content publishing option | Content specialist & front-end | bar: Week 4 Thu to Week 5 Mon
Setup page back-end | Back-end | bar: Week 4 Fri to Week 5 Thu
Code Front-end | Front-end | bar: Week 5 Mon to Week 6 Mon
Customer presentation & approval | Project manager
PRODUCTS | bar: Week 4 Thu to Week 7 Tue
Create catalogue/product display design | Visual designer | bar: Week 4 Thu to Week 5 Mon
Prepare product images | Content specialist | bar: Week 4 Thu to Week 5 Mon
Create/prepare product descriptions | Content specialist | bar: Week 5 Tue to Week 5 Fri
Code catalogue | Back-end & Front-end | bar: Week 5 Fri to Week 6 Wed
Create & code sorting function | Back-end & Front-end | bar: Week 6 Tue to Week 6 Fri
Create and code automatic Toplist viewer | Back-end & Front-end | bar: Week 7 Mon
Customer presentation & approval | Project manager
PURCHASE | bar: Week 7 Wed to Week 9 Mon
Create shopping cart function | Back-end & Front-end | bar: Week 7 Wed to Week 7 Thu
Add features for easy product handling | Back-end & Front-end | bar: Week 7 Fri to Week 8 Mon
Create shopping cart overview with possibility to change products directly | Back-end & Front-end | bar: Week 8 Tue
Create a purchase overview available in also profile | Back-end & Front-end | bar: Week 8 Wed
Save all purchase data and history | Back-end | bar: Week 8 Thu to Week 8 Fri
Customer presentation & approval | Project manager
PAYMENT | bar: Week 8 Wed to Week 9 Fri
Design & code page layout | Front-end & visual designer | bar: Week 8 Wed to Week 9 Thu
Create safe payment options | Back-end | bar: Week 9 Mon to Week 9 Tue
Payment methods | Back-end | bar: Week 9 Wed
Create automated receipt | Back-end | bar: Week 9 Thu
Customer presentation & approval | Project manager
CONTACT | bar: Week 10 Mon to Week 11 Mon
Create contact forms | Back-end & Front-end | bar: Week 10 Mon to Week 10 Tue
Create live chat | Back-end | bar: Week 10 Wed to Week 10 Thu
Add contact info to page & footer | Front-end | bar: Week 10 Wed
Make Q&A page | Front-end & visual designer & content specisalist | bar: Week 10 Thu to Week 10 Fri
Customer presentation & approval | Project manager
GRANDE FINALE | bar: Week 11 Tue to Week 12 Fri
Bugtest | Back-end & Front-end | bar: Week 11 Tue to Week 11 Thu
Bugfix | Back-end & Front-end | bar: Week 11 Fri to Week 12 Tue
Pre-release | Back-end & Front-end | bar: Week 12 Wed
Page release | Back-end & Front-end | bar: Week 12 Thu
Customer overtake | Project manager